## Slide 1
FirstBank
DIGITAL FACTORY
TAKE-HOME TASK · SCRUM MASTER
NovaLend Scrum Master Ops Kit
A plan to get a squad that has missed two sprints to a CBN regulatory reporting deadline that cannot move — Friday 30 October 2026
Prepared by Deborah Agbanimu· Scrum Master, NovaLend · 16 September 2026
Product scenario: FirstBank NovaPay · Plan window: Mon 21 Sep – Fri 30 Oct 2026
CBN DEADLINE
30 Oct
6 weeks · 29 working days
Notes: Opening line: this kit is written for one team, one date and one history. Every number in it traces back to the scenario: 7 people, a contractor 5 hours behind Lagos, two missed sprints, a CBN date on Friday 30 October 2026, and a NovaWallet API that has slipped before. Team member names are illustrative for the exercise.

## Slide 2
CONTEXT
The situation every artifact in this kit is built around
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
2
7
people in the squad
4 engineers · 1 QA · 1 designer · 1 PO
5h
contractor behind Lagos
Toronto (EDT) — gap holds to 1 Nov, after the deadline
2
sprints missed in a row
Committed 34 & 32 pts · delivered 21 & 19
30 Oct
CBN reporting deadline
Fixed · 6 weeks · 29 working days
1
blocking dependency
NovaWallet Ledger Events API v2 — history of slipping
Name | Role | Location · working hours (WAT) | What matters for this plan
Adaeze Okafor | Product Owner | Lagos · 09:00–17:00 | Owns scope trade-offs and the Compliance relationship
Tunde Bakare | Backend engineer · tech lead | Lagos · 09:00–17:00 | Technical contact for the NovaWallet squad
Chiamaka Eze | Backend engineer | Lagos · 09:00–17:00 | Knows repayment & reconciliation logic · approved leave 12–16 Oct
Ifeoluwa Adeyemi | Frontend engineer | Lagos · 09:00–17:00 | Compliance review screen
Daniel Mensah | Backend engineer (contractor) | Toronto · 14:00–22:00 WAT | Ingestion service · only 3h overlap with Lagos (14:00–17:00)
Halima Yusuf | QA engineer | Lagos · 09:00–17:00 | Sole tester on a regulator-facing release
Kelechi Nwosu | Product designer | Lagos · ~30% on CBN scope | Review screen using existing NovaPay design system
Names are illustrative for this exercise. Sprint history figures are the baseline I'd verify in Jira on Day 1 before planning.

## Slide 3
README
What's where — and which assessment criterion each part answers
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
3
Artifact | Slides | What you'll find | Assessment criterion
1 · 6-week plan | 4–8 | Week-by-week timeline, capacity maths (holiday + leave), protect/defer/cut decisions, burn-up, ceremony cadence | Situational specificity
2 · RAID log | 9–10 | 13 entries — 6 risks, 2 assumptions, 3 issues, 2 dependencies — each with owner, severity, mitigation, date | Risk & dependency management
3 · Retro facilitation plan | 11–13 | Reset retro agenda, the exact questions, dominant/quiet-voice tactics, how output becomes owned actions | Facilitation quality
4 · Stakeholder comms plan | 14–15 | Weekly / monthly / one-off audiences, and a fully written W3 status update with a decision request | Stakeholder communication
5 · Ceremony redesign | 16–17 | Standup, planning and retro rebuilt around the 14:00–17:00 overlap; Tuesday 6 October walked hour by hour | Situational specificity
6 · Dependency map | 18–19 | Map of the NovaWallet API dependency, fallback path, RAG rules and 4-level escalation ladder | Risk & dependency management
Stretch goals | 7, 19, 20 | Burn-up & capacity charts · escalation script (exact words) · regulator-facing Definition of Done | Differentiators
Defending the plan | 21 | The six pushbacks I expect from leadership and my answers | Communication & defensibility
AI_USAGE | 22 | Tools, prompts, and the review checks used to catch generic AI output | AI fluency & judgment

## Slide 4
ARTIFACT 1 · 6-WEEK PLAN
Six weeks to Friday 30 October — submit on the 28th, keep 2 days' buffer
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
4
SPRINT 1 · 21 Sep – 2 Oct · 9 working days · commit 15 pts
SPRINT 2 · 5 – 16 Oct · commit 14 pts
SPRINT 3 · 1 week · 9 pts
HARDENING · no new scope
Week 1
Mon 21 – Fri 25 Sep
Mon: reset retro (90 min)
Tue: Sprint 1 planning at 15 pts, not 34
Tue–Thu: refinement blitz
Wed: CBN field mapping walkthrough with Compliance
Fri: NovaWallet API contract signed
◆ Scope + API contract locked
Week 2
Mon 28 Sep – Fri 2 Oct
Thu 1 Oct: Independence Day — no work
Build on NovaWallet mock server
Chiamaka starts pairing Daniel on reconciliation
Fri: review — sample extract shown to Compliance
◆ NovaWallet API in staging (due Fri 2 Oct)
Week 3
Mon 5 – Fri 9 Oct
Mon: Sprint 2 planning
Mon 5: monthly update to Head of Digital Factory
Wed 7: reconciliation handover recorded
Fri 9, 12:00: API vs fallback go/no-go
◆ Dependency decision point
Week 4
Mon 12 – Fri 16 Oct
Chiamaka on approved leave (5 days)
Thu 15: first end-to-end dry run
Fri 16: Sprint 2 review — Compliance sample sign-off #1
◆ NovaWallet API in production (due Fri 16 Oct)
Week 5
Mon 19 – Fri 23 Oct
Reconcile on masked production-like data
Wed–Thu: Compliance UAT
Fri: short review + 45-min retro
◆ Feature freeze Fri 23 Oct
Week 6
Mon 26 – Fri 30 Oct
Mon–Tue: full regression + re-run test
Tue 27: final Compliance sign-off + CAB
Wed 28: submit to CBN
Thu–Fri: buffer; retro Fri 30
◆ CBN deadline Fri 30 Oct
Why Sprint 3 is one week: the last five working days are held for regression, sign-off and change approval. Submitting on deadline day is not a plan — if anything breaks on the 28th, we still have the 29th and 30th.
Notes: Defending the sprint shape: two-week sprints keep ceremony overhead low for a team that is already stretched; Sprint 3 is shortened so Week 6 is clean. Hard dates: API contract 25 Sep, staging 2 Oct, go/no-go 9 Oct 12:00, prod 16 Oct, freeze 23 Oct, sign-off 27 Oct, submission 28 Oct, deadline 30 Oct.

## Slide 5
ARTIFACT 1 · 6-WEEK PLAN
Capacity: planned on what the team delivered, not what it committed
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
5
Week | Working days | Engineer-days | Deductions | Forecast pts
W1 | 5 | 20 | — | 10
W2 | 4 | 16 | Independence Day, Thu 1 Oct (−4) | 8
W3 | 5 | 20 | — | 10
W4 | 5 | 15 | Chiamaka approved leave 12–16 Oct (−5) | 7.5
W5 | 5 | 20 | — | 10
W6 | 5 | 20 | Hardening — regression & fixes only | 0 new
Total | 29 | 111 | −9 engineer-days | 45.5
4 engineers incl. Daniel at full capacity — the 3h overlap is a collaboration constraint, not lost hours. Halima (QA): 29 days. Kelechi: ~9 days at 30%.
Chart: Engineer-days available per week
| W1 | W2 | W3 | W4 | W5 | W6
Engineer-days | 20 | 16 | 20 | 15 | 20 | 20
0.5 pts / engineer-day
Last two sprints delivered 21 and 19 pts on 40 engineer-days each. That number already includes meetings, support and context-switching — so no second focus-factor haircut.
45.5 pts forecast
0.5 × the 91 build engineer-days in W1–W5. Week 6 adds no new scope: its 20 engineer-days go to regression, defect fixes and submission support.
38 pts committed (84%)
7.5 pts held back to absorb a NovaWallet slip or production support. After committing 34 and delivering 21, the team needs to see a plan it can actually hit.

## Slide 6
ARTIFACT 1 · 6-WEEK PLAN
Trade-offs: what gets protected, deferred and cut — and why
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
6
Original quarter backlog: 61 pts Forecast capacity: 45.5 pts Committed to CBN scope: 38 pts Moved out: 23 pts
PROTECT · 38 pts
Everything the CBN report needs to be correct and auditable
8 | NovaWallet Ledger Events integration (idempotent, retries)
8 | Repayment & days-past-due (DPD) engine
5 | Loan-level data model & CBN field mapping
5 | Regulatory extract generator + schema validation
5 | Reconciliation vs loan book + exception report
3 | Audit trail & immutable report snapshots
2 | Compliance review & approval screen
2 | Submission runbook + job-failure alerting
DEFER to November · 18 pts
Real value, no regulatory date
5 | Borrower loan-statement redesign — customer polish; frees Kelechi for the review screen
8 | BNPL merchant onboarding (NovaBiz) — revenue, not regulation; PO resets expectations 23 Sep
5 | Credit model v2 tuning — changing scoring mid-build changes the loans we're reporting on
CUT / DE-SCOPE · 5 pts
Replaced by something simpler
3 | Automated CBN portal submission → manual upload with four-eyes checklist on 28 Oct; automate in Nov
2 | Leadership analytics dashboard → CSV export; no one outside Compliance needs it before 30 Oct
Protected under any pressure: reconciliation to ₦0 variance · audit trail · full regression on disbursement & repayment · named Compliance sign-off · no planned weekend work. After two missed sprints, overtime would spend the trust this plan is trying to rebuild. Deferred ≠ dropped: all 18 pts sit at the top of the November backlog.

## Slide 7
ARTIFACT 1 · 6-WEEK PLAN · STRETCH: BURN-UP
Burn-up to the deadline — and the order I cut in if we fall behind
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
7
Chart: Story points — plan vs capacity
| W1 | W2 | W3 | W4 | W5 | W6
Original backlog (61) | 61 | 61 | 61 | 61 | 61 | 61
Forecast capacity (cumulative) | 10 | 18 | 28 | 35.5 | 45.5 | 45.5
Committed scope (38) | 38 | 38 | 38 | 38 | 38 | 38
Planned done (cumulative) | 8 | 15 | 23 | 29 | 38 | 38
Tracked every Thursday 16:00 WAT from Jira; W6 is flat by design (hardening). At W5 the 7.5-pt gap between forecast capacity and planned done is the buffer.
If we slip, cut in this order
1
Trigger: Burn-up >4 pts behind plan at end of W3
Replace the Compliance review screen with a sign-off form + restricted folder (−2 pts)
2
Trigger: NovaWallet API not in staging by Fri 9 Oct, 12:00
Switch to nightly ledger extract fallback; API integration moves to November (−8 pts, +3 pts)
3
Trigger: Still behind at Sprint 2 review, Fri 16 Oct
Job-failure alerting becomes a manual daily check in the runbook (−1 pt)
4
Trigger: Protected items themselves at risk on 23 Oct
Nothing else is cut. Head of Digital Factory and Compliance are told the same day — not on 29 Oct
Triggers are agreed with Adaeze (PO) on 22 Sep, so cutting is a pre-made decision, not a debate under stress.

## Slide 8
ARTIFACT 1 · 6-WEEK PLAN
Ceremony cadence — live sessions sit inside the 3-hour overlap
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
8
Ceremony | When (WAT) | Toronto (EDT) | Length | Who | Why it's set up this way
Daily standup | Mon–Fri 14:15 | 09:15 | 15 min | Squad; PO optional | Old 09:30 slot was 04:30 for Daniel — he missed live decisions for two sprints
Sprint planning | Tue 22 Sep, Mon 5 Oct, Mon 19 Oct · 14:00 | 09:00 | 2.5h (S3: 1h) | Squad + PO | Goal & top stories posted Fri; async comments by Mon 12:00; live time for sizing and commitment
Refinement | Wed 15:00, first week of sprint | 10:00 | 60 min | PO, Tunde, Halima, Daniel, Kelechi | ~40% of CBN stories lack acceptance criteria — nothing enters a sprint without AC + test notes
NovaWallet dependency sync | Tue 11:00 | 06:00 (not required) | 30 min | Deborah, Tunde, NovaWallet SM + lead | Notes posted by 12:00 with @Daniel tags; RAG feeds Thursday update
Sprint review | Fri 2, 16, 23 Oct · 14:00 | 09:00 | 60 min | Squad + Compliance analyst | Regulator-facing: Compliance sees working output every sprint, not in W6
Retrospective | Mon 21 Sep (reset) · Fri 2, 16, 23, 30 Oct · 15:15 | 10:15 | 75 min (23 Oct: 45) | Squad + PO | Miro board opens Wednesday so everyone can add input before the live session
Burn-up check | Thu 16:00 (Wed 30 Sep, holiday week) | 11:00 | 15 min | Deborah, Adaeze, Tunde | Checks cut-order triggers; feeds 17:00 leadership update
Leadership update | Thu 17:00 (written) | — | — | Deborah → Eng leadership | Format and sample on slides 14–15

## Slide 9
ARTIFACT 2 · RAID LOG
RAID log (1 of 2) — risks that could cost us 30 October
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
9
ID | Type | Description | Severity | Owner | Mitigation / next action | Date
R1 | Risk | NovaWallet Ledger Events API v2 misses staging (due Fri 2 Oct). Squad has slipped before; without it there is no repayment data for the report | High | Deborah Agbanimu (SM) | Signed OpenAPI contract by 25 Sep; Daniel builds on a mock from W1; go/no-go Fri 9 Oct 12:00 → nightly extract fallback; escalation ladder (slide 19) | Weekly Tue; decide 9 Oct
R2 | Risk | Our reading of CBN field definitions (DPD buckets, restructured loans) differs from Compliance's → rework discovered in W5 | High | Adaeze Okafor (PO) | Field-by-field walkthrough with Compliance Wed 23 Sep; sample extract reviewed at Sprint 1 review Fri 2 Oct | 23 Sep / 2 Oct
R3 | Risk | A third missed sprint breaks morale; unplanned overtime to 'catch up' leads to burnout or someone leaving before 30 Oct | High | Deborah Agbanimu (SM) | Commit at ~85% of delivered velocity; no planned weekend work; 1:1s with all 7 in W1; make the Sprint 1 win visible | 1:1s by 25 Sep
R4 | Risk | Reconciliation knowledge sits with Chiamaka, who is on approved leave 12–16 Oct in the middle of Sprint 2 | Medium | Tunde Bakare (tech lead) | Daniel pairs on reconciliation 28 Sep–9 Oct in the overlap window; recorded walkthrough + handover doc | 7 Oct
R5 | Risk | One QA engineer on a regulated release; testing piles up at sprint end — a likely contributor to both misses | High | Halima Yusuf (QA) | WIP limit of 2 in 'Ready for QA'; engineers ship API tests in the same PR; test cases written at refinement | Checked Thu
R6 | Risk | Daniel's PRs wait overnight for Lagos review, adding roughly a day to every change he makes | Medium | Tunde Bakare (tech lead) | Daniel's PRs reviewed by 12:00 WAT next day; named Lagos review buddy; live reviews 14:30–17:00 | From 22 Sep
A1 | Assumption | 'Ready' = validated loan-level extract + reconciliation + Compliance sign-off, uploaded manually — not an automated CBN integration | High if wrong | Adaeze Okafor (PO) | Confirm in writing with Compliance on 23 Sep. If wrong, re-plan scope that same week while there's room | 23 Sep

## Slide 10
ARTIFACT 2 · RAID LOG
RAID log (2 of 2) — assumptions, issues and dependencies
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
10
ID | Type | Description | Severity | Owner | Mitigation / next action | Date
A2 | Assumption | Masked production-like loan data is available in UAT by Wed 14 Oct for the first end-to-end dry run | Medium | Tunde Bakare (tech lead) | InfoSec request raised Tue 22 Sep; synthetic dataset built in Sprint 1 so the dry run can run on it if approval is late | 14 Oct
I1 | Issue | Two consecutive missed sprints: committed 34 and 32 pts, delivered 21 and 19. Commitments were set on hope, not data | High | Deborah Agbanimu (SM) | Re-baseline on delivered velocity (0.5 pts/engineer-day); reset retro Mon 21 Sep; burn-up visible on the team board | 22 Sep
I2 | Issue | About 40% of CBN stories have no acceptance criteria or test notes — Halima can't test what isn't defined | High | Adaeze Okafor (PO) | Refinement blitz 22–24 Sep; rule: no story enters a sprint without AC + test notes | 24 Sep
I3 | Issue | 09:30 WAT standup is 04:30 for Daniel; he has been excluded from live decisions for two sprints | Medium | Deborah Agbanimu (SM) | Move standup to 14:15 WAT from 22 Sep; decisions logged in #novalend-decisions | 22 Sep
D1 | Dependency | NovaWallet Ledger Events API v2 (disbursement, repayment, reversal events) — staging Fri 2 Oct, production Fri 16 Oct | High | Segun Alabi (NovaWallet EM) · tracked by Deborah | On NovaWallet's sprint board as a committed item; contract tests in CI; RAG in Tue sync and Thu update | 2 Oct / 16 Oct
D2 | Dependency | Compliance/Risk availability for sign-off: sample on Fri 16 Oct, final on Tue 27 Oct | High | Adaeze Okafor (PO) | Calendar slots booked on 23 Sep with a named approver and a named deputy | 23 Sep

## Slide 11
ARTIFACT 3 · RETRO FACILITATION PLAN
Reset retro — built so it doesn't end in 'we'll estimate better' again
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
11
Mon 21 Sep · 14:00–15:30 WAT / 09:00–10:30 Toronto · Meet + Miro, own laptops · Squad + PO (7) · Facilitator: Deborah · No managers
Before the room
Thu 17 Sep — anonymous 3-question form
(no sign-in; Daniel answers on his own time)
1. On Day 1 of the last two sprints, how confident were you in the commitment? (1–5)
2. What slowed you down that nobody says out loud?
3. What's one thing you'd stop doing tomorrow?
Fri 18 Sep — 20-min 1:1s with Tunde and Adaeze
The two strongest voices. I ask them to speak last and help me hear others.
Fri 18 Sep — pull the facts from Jira
Committed vs delivered, time in each board column, carried-over tickets — pinned on the Miro timeline so we argue about data, not memory.
10'
Set the stage
Say what this isn't: not a post-mortem on people, not a performance review. I'm new — 'help me understand'. Anonymous ESVP check-in (Explorer / Shopper / Vacationer / Prisoner) and survey headlines.
25'
Gather data
Two-sprint timeline on Miro. 8 min silent writing: green = helped, red = hurt, blue = work waited. Then 1-2-4-All on 'where did work wait longest?' (Daniel paired with Halima in a breakout).
25'
Generate insights
Cluster sticky notes, 3 dots each. Top 2 themes go through Circles & Soup: what we control, what we influence, what's soup (NovaWallet's roadmap, the CBN date).
20'
Decide
Maximum 3 experiments, only from 'control' or 'influence'. Each needs a volunteer owner, a date inside Sprint 1 and a visible check.
10'
Close
Return on Time Invested (1–5), optional one-line appreciation, confirm who gets a follow-up 1:1 this week.

## Slide 12
ARTIFACT 3 · RETRO FACILITATION PLAN
The questions I'll ask — and how I handle who talks and who doesn't
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
12
Questions, word for word
1
“On Day 1 of each missed sprint, what did we already know that made 34 points unlikely?”
2
“Where did work sit waiting longest — build, code review, QA, or NovaWallet?”
3
“When did you first think we'd miss? What happened to that signal?”
4
“Daniel — which decisions did you only find out about the next morning?”
5
“Of the reasons we missed, which were genuinely NovaWallet, and which were ours?”
6
“It's 30 October. We submitted on time and nobody burnt out. What did we do differently from the last two sprints?”
If one voice dominates
Before: 1:1s with Tunde and Adaeze — ask them to speak last on each topic
Structure does the work: silent writing before any talking; round-robin with 60-second turns
In the moment: “Tunde, that's useful — hold it. I want Halima and Daniel first.”
PO and I don't dot-vote on commitment topics — the power gradient is real
Deep technical debates go to a parking lot + 30-min follow-up this week
Drawing out quiet voices
Anonymous survey read back as themes, never attributed
Daniel speaks first in every round-robin — remote people otherwise go last, or not at all
Pairs before plenary; low-stakes openers (“What surprised you?”)
Everyone on their own laptop, same Miro board — no conference-room screen that makes Daniel a face on the wall
1:1 within 48h with anyone who said little: “What didn't you want to say in the room?”

## Slide 13
ARTIFACT 3 · RETRO FACILITATION PLAN
Turning retro output into owned actions with dates
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
13
Top 2 dot-voted themes
Circles & Soup: keep only 'control' and 'influence'
≤3 experiments · a named owner · a date · a visible check
Illustrative output — the real list comes from the room. This is what 'good' looks like if the themes are 'over-commitment' and 'work waiting in QA':
# | Experiment | Owner | By | How we'll know it worked
1 | Commit Sprint 1 at 15 pts based on delivered velocity; sprint goal: 'sample CBN extract from mock data, reviewed by Compliance' | Adaeze Okafor (PO) | Tue 22 Sep | Sprint 1 closes 15/15 on Fri 2 Oct
2 | WIP limit of 2 in 'Ready for QA'; engineers write API tests in the same PR instead of handing off | Halima Yusuf | Tue 22 Sep | QA column ≤2 at every Thursday burn-up check
3 | Lagos reviews Daniel's PRs by 12:00 WAT next day; review buddy rota set | Tunde Bakare | Wed 23 Sep | Median PR wait < 1 working day by Fri 2 Oct
SM | Move standup to 14:15 WAT; set up #novalend-decisions. Logistics I own — it doesn't use up one of the team's three experiment slots | Deborah Agbanimu | Tue 22 Sep | Daniel at 5/5 standups in Week 1
On the board
Each action becomes a Sprint 1 ticket labelled retro-action — visible in standup, not in a doc no one opens.
Posted within 1 hour
Summary in #novalend: themes, 3 experiments, owners, dates. Daniel sees it in his own working hours.
Checked first
The next retro (Fri 2 Oct) opens with 5 minutes: each experiment kept, changed or dropped — with the evidence.

## Slide 14
ARTIFACT 4 · STAKEHOLDER COMMS PLAN
Right information, right audience, right cadence
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
14
WEEKLY
Engineering leadership
Head of Engineering · NovaLend EM · NovaWallet EM
When | Thursdays 17:00 WAT, 24 Sep → 29 Oct (6 updates)
Channel | Email, linked in #df-eng-leads
They get | RAG + reason · burn-up vs plan · NovaWallet status vs need-by date · top 3 risks, each with an ask · decisions needed, with a deadline
Leave out | Story-level detail; anything about individual performance
Format | One screen. Decision first. Sample on next slide
MONTHLY
Head of Digital Factory
Via DF leadership meeting
When | Mon 5 Oct (5-min slot + 1-pager) · Mon 2 Nov (post-submission)
Exception | Same-day call if the 23 Oct feature freeze is at risk
They get | Confidence in 30 Oct (High/Med/Low) and why · regulatory exposure · what was deferred to protect the date · cross-squad priority calls needed
Leave out | Story points, velocity, sprint mechanics
Format | 1 page; three sentences at the top they could repeat upward
ONE-OFF
Compliance / Risk
Head of Compliance + named approver
When | Wed 23 Sep, after the field-mapping walkthrough
Channel | Formal email from PO + SM; sign-off slots sent as invites
They get | What 'ready' means for submission (A1) · deadline risk rating: Amber · biggest risk (NovaWallet) + fallback and its 9 Oct decision date · what we need from them: 23 Sep, 16 Oct, 27 Oct
Trigger | If freeze slips past 23 Oct they hear within 24h, so they can decide whether to engage CBN early
Leave out | Technical implementation detail

## Slide 15
ARTIFACT 4 · SAMPLE WEEKLY STATUS UPDATE
Sample weekly update — Week 3, Thursday 8 October 2026
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
15
To: Head of Engineering Cc: NovaLend EM, Segun Alabi (NovaWallet EM), Adaeze Okafor (PO)
Subject: [AMBER] NovaLend CBN reporting — W3 status — decision needed by Fri 9 Oct, 12:00 WAT
BOTTOM LINE
AMBER. Our own build is on plan. Fri 30 Oct is at risk for one reason: NovaWallet's Ledger Events API v2 missed staging (due 2 Oct); their new date is Wed 14 Oct.
DECISION NEEDED — Head of Engineering, by Fri 9 Oct 12:00 WAT
A (recommended): approve the nightly ledger-extract fallback now. Cost: 1 NovaWallet engineer × 2 days (12–13 Oct) + read-replica access from Data Platform; 3 pts for us. API integration moves to November.
B: wait for 14 Oct. Integration then needs ~6 engineer-days inside Sprint 3, leaving zero buffer before the 23 Oct freeze. One more slip and we miss CBN.
No decision by 12:00 → we prepare A on our side only (no NovaWallet effort spent) so the weekend isn't lost. Segun agrees with this recommendation.
PROGRESS
19 of 38 committed pts done; plan for Fri is 23. 3 pts in QA → expect 22 by Fri close (1 pt behind, within buffer). Sprint 1 delivered 15/15 — first sprint met in three. CBN field mapping signed off by Compliance 6 Oct; DPD engine passing all 42 test cases on the mock.
NEXT WEEK (12–16 Oct)
Reconciliation job + extract generator; first end-to-end dry run Thu 15 Oct. Chiamaka on approved leave — reconciliation handed to Daniel (walkthrough recorded 7 Oct).
RISKS & ASKS
1. NovaWallet API — High — decision above.
2. Masked UAT data — Medium — InfoSec ticket SEC-2291 open since 22 Sep, needed by 14 Oct. Ask: please nudge the InfoSec lead today.
3. QA load in Sprint 3 — Medium — WIP limit holding (queue at 2). No action needed.
Next update Thu 15 Oct, 17:00 WAT · Deborah Agbanimu, Scrum Master, NovaLend
Why a lead can act on this without a meeting
Decision first
What, who decides, by when — and what happens if nobody answers.
Options are costed
People-days, access and consequence, so the choice needs no follow-up call.
Numbers vs plan
19 vs 23 planned tells them how worried to be; '50% done' wouldn't.
Every risk has an ask
Or says 'no action needed', so leaders don't guess.
No surprise for NovaWallet
Segun is cc'd and already agreed — this isn't escalating around him.

## Slide 16
ARTIFACT 5 · CEREMONY REDESIGN
Redesigned so Daniel takes part live — not 'catch up async'
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
16
Standup
BEFORE 09:30 WAT = 04:30 in Toronto. Daniel posted written updates nobody read, and blockers waited a day.
AFTER
14:15 WAT / 09:15 Toronto, 15 min, walk the board right-to-left
Facilitator rotates — Daniel runs Thursdays
His blockers are worked in the 14:30–17:00 window, same day
Lagos cost, acknowledged: #novalend-blockers triaged by me at 10:00
Sprint planning
BEFORE Mon 10:00 WAT. Daniel was handed tasks afterwards and never sized his own work.
AFTER
PO posts goal + top stories Fri 15:00 WAT
Everyone comments in the doc by Mon 12:00 WAT — Daniel on Friday afternoon his time
Live 14:00–16:30 WAT only for sizing debates and commitment
Daniel breaks down the ingestion stories live
Retro & review
BEFORE Friday morning. Daniel joined the retro at 05:00 or not at all; Lagos engineers demoed his work.
AFTER
Retro Fri 15:15 WAT / 10:15 Toronto; Miro opens Wed
Daniel speaks first in every round; everyone on own laptop
Review 14:00 WAT — Daniel demos his own work to Compliance
At least one action co-owned by Daniel when it touches his area
Team agreements that make it work
① 14:30–17:00 WAT is protected — no external meetings for the squad. ② Decisions touching Daniel's area go in #novalend-decisions and become final after one of his working sessions, unless deadline-critical. ③ Daniel posts a handoff by 21:30 WAT; Lagos answers by 10:00. ④ His PRs are reviewed by 12:00 WAT next day.

## Slide 17
ARTIFACT 5 · ONE CONCRETE DAY
One concrete day: Tuesday 6 October 2026 (Sprint 2, Day 2)
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
17
08:00
03:00
09:00
04:00
10:00
05:00
11:00
06:00
12:00
07:00
13:00
08:00
14:00
09:00
15:00
10:00
16:00
11:00
17:00
12:00
18:00
13:00
19:00
14:00
20:00
15:00
21:00
16:00
22:00
17:00
23:00
18:00
WAT
Toronto
Lagos squad
Daniel (Toronto)
Review Daniel's PRs
Build
NovaWallet sync + notes
Build
Lunch
Collaboration window: pairing, live PR reviews, design & QA questions
Offline
Offline (03:00–09:00 Toronto)
Pairs with Chiamaka on reconciliation handover
Focus: ingestion retries & idempotency
Offline
14:15 live standup
Overlap 14:00–17:00 WAT
21:30 handoff post
09:10 WAT
Tunde approves Daniel's idempotency PR from last night. Halima picks up the overnight staging build before standup.
11:30 WAT
NovaWallet sync: still no staging date. Notes posted with @Daniel: 'keep building against mock v2.1'. RAG → Amber for Thursday.
14:15 WAT
Daniel flags that the mock and contract disagree on repayment reversals. Fixed with Tunde at 14:40 in the window — not overnight.
21:40 WAT
Daniel's handoff: 1 PR up, 1 question for Halima on reversal test data. Lagos picks it up at 09:00 Wednesday.
Result: every live decision today happened while Daniel was in the room. His longest wait for a Lagos answer is the ~11h overnight gap — down from a full day or more when standup was at 04:30 his time.

## Slide 18
ARTIFACT 6 · DEPENDENCY MAP
NovaLend's dependency on the NovaWallet API — and how it's managed
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
18
NOVAWALLET SQUAD
NOVALEND SQUAD
REGULATORY
NovaWallet core ledger
Ledger Events API v2
disbursement · repayment · reversal
Staging 2 Oct · Prod 16 Oct
FALLBACK
Nightly ledger extract from read replica · decide Fri 9 Oct 12:00
Ingestion service
Daniel
Repayment & DPD engine
Chiamaka → Daniel (12–16 Oct)
Loan-level store + audit trail
Extract generator + reconciliation
Freeze 23 Oct
Compliance sign-off
16 Oct · 27 Oct
CBN submission
Wed 28 Oct
Deadline Fri 30 Oct
BLOCKING
How I manage it
1
Contract first
OpenAPI v2 spec signed by both tech leads by Fri 25 Sep; any change needs both approvals.
2
Don't wait
Daniel builds on a mock of the signed spec from W1; contract tests run nightly in CI against staging once it exists.
3
Need-by dates on their board
Staging 2 Oct and prod 16 Oct sit on NovaWallet's sprint board as committed items, reviewed at Tuesday's sync.
4
Fallback agreed in advance
Nightly extract costs us 3 pts and NovaWallet 2 engineer-days. Decision point Fri 9 Oct 12:00 — not later.
5
RAG rule
Green: on date. Amber: date moved or contract tests failing >1 day. Red: need-by date passed with no committed new date → Level 2 same day.
Notes: Mermaid source for the repo version of this map: flowchart LR subgraph NovaWallet squad L[Core ledger] --> API[Ledger Events API v2 staging 2 Oct · prod 16 Oct] FB[Fallback: nightly ledger extract decide Fri 9 Oct 12:00] end subgraph NovaLend squad ING[Ingestion service] --> DPD[Repayment & DPD engine] DPD --> STORE[Loan-level store + audit trail] STORE --> EXT[Extract generator + reconciliation freeze 23 Oct] end subgraph Regulatory CMP[Compliance sign-off 16 Oct · 27 Oct] --> CBN[CBN submission 28 Oct deadline 30 Oct] end API -- BLOCKING --> ING FB -. if API late .-> ING EXT --> CMP classDef block stroke:#B42318,stroke-width:3px; class API block;

## Slide 19
ARTIFACT 6 · ESCALATION · STRETCH: ESCALATION SCRIPT
Escalating a blocking NovaWallet delay — the ladder and the exact words
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
19
L0
Squad to squad · same day
Tunde ↔ NovaWallet tech lead
Contract test fails or date wobbles. Aim: a fix or a new date in writing today.
L1
Scrum Masters / EMs · within 2 working days
Deborah ↔ Segun Alabi (NovaWallet EM)
New date lands after our need-by. Output: joint recovery plan, logged as D1.
L2
Engineering leadership · by Fri 9 Oct, 12:00
Head of Engineering + both EMs
No committed staging date by 9 Oct. Output: fallback approved or NovaWallet re-prioritised.
L3
Head of Digital Factory · within 48h
Compliance informed in parallel
L2 unresolved, or the 23 Oct freeze is at risk. Output: cross-squad priority call.
Rule: NovaWallet's EM hears every escalation from me before anyone above him does. Escalation is a scheduled event with a pre-agreed trigger — not a complaint.
L1 · To Segun (NovaWallet EM), on a call — Mon 5 Oct
“Segun, I'd rather flag this early than surprise you. Our CBN report for 30 October depends on Ledger Events v2 being in staging — it was due on the 2nd and it isn't there yet. I know you have your own pressures. Can we agree today on a date you're confident in, not an optimistic one? Our last safe date is Friday the 9th at noon. If that can't happen, I'd like us to take the fallback to [Head of Engineering] together on Thursday — a nightly ledger extract, about two days of one of your engineers — so it's our joint recommendation, not me going around you.”
L2 · To Head of Engineering, Thu 8 Oct — with Segun on the call
“We need a decision from you by Friday at 12:00. NovaWallet's API has missed staging, and their new date of the 14th leaves no buffer before our 23 October freeze on a CBN date that can't move. Segun and I both recommend the nightly extract fallback — it costs one of his engineers two days. If we wait and it slips once more, we miss the regulator.”

## Slide 20
STRETCH GOAL · DEFINITION OF DONE
Definition of Done — tightened for a regulator-facing deliverable
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
20
Standard DoD — still applies
Acceptance criteria met
Code reviewed and merged
Automated tests green in CI
Deployed to staging
No open Sev 1 / Sev 2 defects
Docs and runbook updated
For CBN stories, 'done' also means everything on the right. Applies to all 8 protected backlog items; a story that meets only the left column stays in 'Ready for sign-off', not 'Done'.
Data correctness
☐ Every report field traces to a source field + transformation rule in the versioned mapping doc, approved by Compliance
☐ Reconciles to the loan book: loan count, principal outstanding and DPD buckets match to ₦0; each exception has a named explanation
☐ Tested on the cases that break regulatory reports: partial repayment, NovaWallet reversal, restructured loan, in-period write-off, missing BVN
☐ Re-running the same period produces an identical file
Evidence & audit
☐ Test evidence (run IDs, sample outputs) attached to the ticket — 'passed in QA' is not evidence
☐ Every report run logs who, when, code version and data snapshot hash
☐ Four-eyes: 2 approving reviews, one from outside the author's pair (Daniel's PRs: at least one Lagos reviewer)
Security & privacy
☐ BVN and phone numbers masked in logs and non-production environments
☐ Data encrypted at rest and in transit
☐ Extract access limited to named Compliance and Ops roles; InfoSec checklist signed
Sign-off & release
☐ Demoed in sprint review with Compliance present
☐ Named Compliance approver signs off — PO acceptance alone is not enough
☐ Change request approved at CAB; rollback and re-submission runbook tested once before 28 Oct

## Slide 21
DEFENDING THE PLAN
Pushback I expect from leadership — and my answers
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
21
“Can't we just add engineers or ask for weekend work?”
New people cost onboarding time on a regulated codebase inside a 6-week window. Weekend work after two missed sprints spends the morale we need in Week 6. The plan works at 38 pts without either.
“Why commit 38 when capacity is 45.5?”
The last two sprints committed 34 and 32 and delivered 21 and 19. The 7.5 pts are the NovaWallet slip absorber — the one risk we've already seen happen.
“Why a manual CBN upload in 2026?”
Automation adds 3 pts and a brand-new failure point on submission day. A four-eyes checklist upload is auditable and proven. We automate in November.
“Why move standup for 7 people because of 1 contractor?”
Daniel owns the ingestion service that everything else depends on. Excluding him from live decisions for two sprints is part of why we missed. 14:15 costs Lagos little.
“Why decide on the fallback by 9 Oct? Just wait.”
Integration + regression is ~6 engineer-days. Working back from the 23 Oct freeze, 9 Oct noon is the last point both options still fit. After that we're choosing by default.
“Won't telling Compliance about risk now cause alarm?”
Compliance owns the CBN relationship. On 23 Sep, with a fallback and a decision date, it's a plan. On 29 Oct, it's an incident.

## Slide 22
AI_USAGE
How AI was used — and how its output was checked
NovaLend Scrum Master Ops Kit · FirstBank Digital Factory · Deborah Agbanimu
22
Tools and what they were used for
Claude (Anthropic): turned the brief into a first full draft of all six artifacts, the stretch goals and this deck
Human review: checked every date, number, owner and audience against the scenario before accepting any slide
Add any other tools you used here (e.g. Copilot in PowerPoint for layout tweaks)
Prompt 1 — as given
“[8 screenshots of the take-home brief] ENSURE TO FOLLOW THE 'How you'll be assessed' ALSO I NEED YOUR ANSWER TO BE REAL AS POSSIBLE AND Prepare your response in MS PowerPoint.”
What came back: a 22-slide draft Ops Kit. Prompts 2–3 (the targeted corrections) and their results are listed in the AI_USAGE.md in the repo.
Checks applied to catch generic or wrong AI output
Does the calendar actually work?
Every date checked against a real 2026 calendar — Independence Day is a Thursday; 30 Oct is a Friday.
Is velocity from delivery, not commitment?
A standard plan sizes sprints from what was committed (34). This one uses what was delivered (21, 19).
Does the time-zone gap hold to the deadline?
Toronto stays on EDT until 1 Nov, so the 5-hour gap is stable through 30 Oct.
Right detail for the right audience?
No story points for the Head of Digital Factory; no implementation detail for Compliance.
Would a real lead need a meeting to act?
The sample update names who decides, by when, the costed options and the default.
Notes: Before submitting: replace the placeholder line in 'Tools' with the tools you actually used, and document in AI_USAGE.md the follow-up prompts you gave and one specific AI draft you corrected (for example, a status update pitched at the wrong audience, or a plan that used committed rather than delivered velocity). The panel will probe this live, so it must be your real experience.